## Sheet1
Project Title: Milestone 6 Release #: 1.0 Sprint #: 6
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a developer, I’d like to have a cleaner codebase, including updated comments, views, and file headers. | Code Cleanup | All | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0
| 2 | As a user or third-party developer, I’d like for the bugs in the official API to be fixed | API Bug Fixes | n/a | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 3 | As a user, I’d like to be able to save/load my current game. | Game Mechanics | n/a | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| 4 | As a user, I’d like to be able to get to an end game state. (fix UI logic bugs) | Fix Game Mechanics | Daniel | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| 5 | As a stakeholder, I’d like to have a presentation explaining the full stack of this application. | Create Presentation | Hiram / Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| 6 | As a developer, I would like to have a direct line of communication with my team | Communicate goals as a team | All | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| 7 | As a developer, I'd like to have complete documentation | Update project documentation and diagrams | All / Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 13 | 11.1429 | 9.2857 | 7.4286 | 5.5714 | 3.7143 | 1.8571 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 13 | 13 | 13 | 12 | 11 | 11 | 10 | 4