## Sheet1
Project Title: Milestone 3 Release #: 0.3 Sprint #: 3
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a user, I'd like to have a game board that updates based on my input. | Implmenet GameController business logic | Daniel Cender | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
| 2 | As a use, I'd like to have a view where I can interact with the board game. | Create Minesweeper Board View | Nathaniel Kumar | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
| 3 | As a developer, I would like to have a Player Stats table to save statistics information about individual players | Create PlayerStats Table | Hiram Viezca | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 4 | As a developer, I would like to have a Game table to preserve game state data for pausing and resuming games | Create Game Table | Hiram Viezca | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 5 | As a developer, I would like to have a direct line of communication with my team | Communicate goals as a team | All | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0
| 6 | As a developer, I'd like to have complete documentation | Update project documentation and diagrams | All | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 14 | 14 | 13 | 7 | 7 | 7 | 1 | 0