## Sheet1
Project Title: Milestone 5 Release #: 0.5 Sprint #: 5
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a developer, I’d like to have a cleaner codebase. | Code Cleanup | Nathaniel / Hiram | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
| 2 | As a user or third-party developer, I’d like to have an API where I can retrieve game information. | Create API Routes | Daniel | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0
| 3 | As a developer, I would like to have a direct line of communication with my team | Communicate goals as a team | All | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| 4 | As a developer, I'd like to have complete documentation | Update project documentation and diagrams | All / Daniel | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 9 | 7.7143 | 6.4286 | 5.1429 | 3.8571 | 2.5714 | 1.2857 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 9 | 9 | 9 | 8 | 7 | 6 | 0 | 0