## Sheet1
Project Title: Milestone 2 Release #: 0.2 Sprint #: 2
| User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day5 | Day 6 | Day 7 | Amounts Left
| 1 | As a developer, I’d like to have initial UI pages for the Logic and Registration features. | Create UI Pages | Nathaniel Kumar | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | As a developer, I’d like to have a clear separation between business logic and data access layers. | Enforce layer separation / refactor | Daniel Cender | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 3 | As a developer, I’d like to have proper form validation and business logic layering | Add data model restrictions | Daniel Cender | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| 4 | As a user I’d like to have the ability to create an account and save information about myself to a database. | Create DAO for User info | Hiram Viezca | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 5 | As a user, I’d like the game to recognize me when I log into the game. | Tie DAO to view layer | Hiram Viezca | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
| 6 | As a developer, I would like to have a direct line of communication with my team | Communicate goals as a team | All | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0
| 7 | As a developer, I'd like to have complete documentation | Update project documentation and diagrams | All | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 13 | 11.1429 | 9.2857 | 7.4286 | 5.5714 | 3.7143 | 1.8571 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 13 | 13 | 9 | 3 | 0 | 0 | 0 | 0